Notes

24-Hour Show

Seth has been recommended for the director, but he has two conflicts

- Solo Show 6:30pm 3/14

- Improv Show 3/15 7:30 pm

Avery suggested adding a co-director to lessen the load on Seth

- Seth is open to it

- maybe someone on the board

- Music director, co-director combo

- Ori and Harper are suggested

  - Paige will reach out to Ori

Choreographer

- Olivia, ask Seth and Ori for ideas.

Show

- Ideally Shrek TYA

  - waiting on approval as an organization from MTI

Possibly ask Pauper for Props from their production of Shrek

- Backup Plan Ideas

  - 12th Night Drag edition

  - Writing our own Jukebox musical

  - Vignettes from 12th night

MISC

Meeting with Pauper tomorrow 2/19 about Banquet

Need to catch up meeting notes on SyncDin

Venue

- Avery requested the amphitheater through 25Live

- Avery received an email from FUPO, ECPI Events, Macalister Staff with the guidelines for the amphitheater.

  - Need to reply to clear up who we are and what we are doing

  - Need to reach out to Danielle

  - Need to fill out FUPO event form

  - They need billing info?

    - ask Leslie about it

- Amphitheater is booked for Saturday but not Friday night because of a conflict

- Rain Concerns

  - Daniel Music Hall

  - Harper Hall

  - Burgiss Theatre

- Cannot play music in the amphitheater after 10 pm

  - 6 pm preview and 9 pm show if we can’t do the midnight

- Where to go for Friday night rehearsal?

  - Classroom

  - Playhouse Studio

To-do

All

David

- Reach out to Olivia about being the choreographer

- Reach out to Danielle

- Reach out to Leslie about billing and CC Avery

- Look into alternate venues for 24 hour show

- Look into where to have Friday rehearsal

- Catch up meeting notes on SyncDin

Paige

Avery

- Reply to event email to clear up who we are and what we are doing

  - ask about rain procedure

- FUPO Event form

Allison

Ciara